## Metadata
field | value
project_id | SYNTHETIC_DEMO
project_name | Synthetic industrial installation
revision_id | DEMO_001
project_start | 2030-01-07
active_calendar | DEMO_CALENDAR
notes | Neutral data created solely for automated testing.

## Systems
system_id | name | family | arrival_date | delivery_state | assembly_location | installation_zone | template_version | enabled | notes
EARLY_ENABLERS | Early enablers | Site preparation | 2030-01-07 | Not applicable | Demo facility | SERVICE_AREA | DEMO_V1 | TRUE | Independent preparation before equipment arrival.
EQUIPMENT_SKID | Equipment skid | Packaged equipment | 2030-01-09 08:00 | Factory assembled | Demo facility | ASSEMBLY_AREA | DEMO_V1 | TRUE | Synthetic equipment with acceptance before availability.

## Packages
package_id | system_id | name | template | enabled | display_order
SITE_PREPARATION | EARLY_ENABLERS | Site preparation | DEMO_SITE_PREP | TRUE | 1
SKID_ACCEPTANCE | EQUIPMENT_SKID | Receipt and acceptance | DEMO_ACCEPTANCE | TRUE | 1
SKID_INSTALLATION | EQUIPMENT_SKID | Installation | DEMO_INSTALLATION | TRUE | 2

## Activities
activity_id | package_id | name | duration_h | duration_basis | preemptible | calendar_id | requires_system_arrival | enabled | template_origin | is_override | notes
PREPARE_FOUNDATION | SITE_PREPARATION | Prepare foundation | 8 | WORK_TIME | FALSE | DEMO_CALENDAR | FALSE | TRUE | DEMO_SITE_PREP | FALSE | Uses the same crew as service routing.
ROUTE_SERVICES | SITE_PREPARATION | Route services to installation boundary | 10 | WORK_TIME | TRUE | DEMO_CALENDAR | FALSE | TRUE | DEMO_SITE_PREP | FALSE | May pause at calendar gaps.
ACCEPT_SKID | SKID_ACCEPTANCE | Inspect and accept delivered skid | 4 | WORK_TIME | FALSE | DEMO_CALENDAR | TRUE | TRUE | DEMO_ACCEPTANCE | FALSE | The skid becomes available only after this activity.
POSITION_SKID | SKID_INSTALLATION | Position equipment skid | 8 | WORK_TIME | FALSE | DEMO_CALENDAR | TRUE | TRUE | DEMO_INSTALLATION | FALSE | Continuous across adjacent crew shifts.
FINAL_CONNECTION | SKID_INSTALLATION | Complete final service connection | 4 | WORK_TIME | FALSE | DEMO_CALENDAR | TRUE | TRUE | DEMO_INSTALLATION | FALSE | Requires both prior routing and final positioning.
SEAL_CURE | SKID_INSTALLATION | Allow connection seal to cure | 24 | ELAPSED_TIME | FALSE |  | TRUE | TRUE | DEMO_INSTALLATION | FALSE | Elapsed time continues outside work shifts.

## Gates
gate_id | system_id | package_id | name | gate_type | exposed | is_project_milestone | notes
SKID_AVAILABLE | EQUIPMENT_SKID | SKID_ACCEPTANCE | Skid accepted and available | AVAILABLE | TRUE | FALSE | Generated by receipt and acceptance.
SKID_POSITIONED | EQUIPMENT_SKID | SKID_INSTALLATION | Skid positioned | READY | TRUE | TRUE | Required before final service connection.
PROJECT_COMPLETE |  |  | Synthetic project complete | PROJECT_COMPLETE | TRUE | TRUE | Final objective for the synthetic project.

## Dependencies
dependency_id | source_type | source_id | target_type | target_id | relation | lag_h | enabled | rationale
DEP_001 | ACTIVITY | ACCEPT_SKID | GATE | SKID_AVAILABLE | FS | 0 | TRUE | Acceptance creates availability.
DEP_002 | GATE | SKID_AVAILABLE | ACTIVITY | POSITION_SKID | FS | 0 | TRUE | Positioning requires accepted equipment.
DEP_003 | ACTIVITY | PREPARE_FOUNDATION | ACTIVITY | POSITION_SKID | FS | 2 | TRUE | Foundation must be complete with elapsed settling lag.
DEP_004 | ACTIVITY | POSITION_SKID | GATE | SKID_POSITIONED | FS | 0 | TRUE | Positioning creates the state.
DEP_005 | ACTIVITY | ROUTE_SERVICES | ACTIVITY | FINAL_CONNECTION | FS | 0 | TRUE | Services can be routed early but must be ready before connection.
DEP_006 | GATE | SKID_POSITIONED | ACTIVITY | FINAL_CONNECTION | FS | 0 | TRUE | Final connection occurs only after positioning.
DEP_007 | ACTIVITY | FINAL_CONNECTION | ACTIVITY | SEAL_CURE | FS | 0 | TRUE | Cure starts after connection.
DEP_008 | ACTIVITY | SEAL_CURE | GATE | PROJECT_COMPLETE | FS | 0 | TRUE | Cure completes the synthetic project.

## Resources
resource_id | name | type | capacity | calendar_id | unlimited | notes
INSTALL_CREW | Installation crew | HUMAN | 1 | DEMO_CALENDAR | FALSE | Shared by enabling and installation work.
INSPECTION_CREW | Inspection crew | HUMAN | 1 | DEMO_CALENDAR | FALSE | Used for delivery acceptance.

## ActivityResources
activity_id | resource_id | quantity
PREPARE_FOUNDATION | INSTALL_CREW | 1
ROUTE_SERVICES | INSTALL_CREW | 1
ACCEPT_SKID | INSPECTION_CREW | 1
POSITION_SKID | INSTALL_CREW | 1
FINAL_CONNECTION | INSTALL_CREW | 1

## ResourceSubstitutions
required_resource_id | substitute_resource_id | conversion_ratio | enabled | notes

## Zones
zone_id | name | capacity | calendar_id | notes
SERVICE_AREA | Service preparation area | 2 |  | Allows limited concurrent work.
ASSEMBLY_AREA | Assembly area | 1 |  | Positioning requires exclusive occupancy.

## ActivityZones
activity_id | zone_id | load | exclusive
PREPARE_FOUNDATION | ASSEMBLY_AREA | 1 | FALSE
ROUTE_SERVICES | SERVICE_AREA | 1 | FALSE
POSITION_SKID | ASSEMBLY_AREA | ALL | TRUE
FINAL_CONNECTION | ASSEMBLY_AREA | ALL | TRUE
SEAL_CURE | ASSEMBLY_AREA | 1 | FALSE

## Calendars
calendar_id | name | timezone | valid_from | valid_to | weekend_days | notes
DEMO_CALENDAR | Synthetic weekday calendar | UTC | 2030-01-01 | 2030-12-31 | SAT,SUN | Two adjacent four-hour shifts form one eight-hour window.

## CalendarShifts
calendar_id | weekday | shift_name | start_time | end_time | enabled
DEMO_CALENDAR | MON | Shift A | 08:00 | 12:00 | TRUE
DEMO_CALENDAR | MON | Shift B | 12:00 | 16:00 | TRUE
DEMO_CALENDAR | TUE | Shift A | 08:00 | 12:00 | TRUE
DEMO_CALENDAR | TUE | Shift B | 12:00 | 16:00 | TRUE
DEMO_CALENDAR | WED | Shift A | 08:00 | 12:00 | TRUE
DEMO_CALENDAR | WED | Shift B | 12:00 | 16:00 | TRUE
DEMO_CALENDAR | THU | Shift A | 08:00 | 12:00 | TRUE
DEMO_CALENDAR | THU | Shift B | 12:00 | 16:00 | TRUE
DEMO_CALENDAR | FRI | Shift A | 08:00 | 12:00 | TRUE
DEMO_CALENDAR | FRI | Shift B | 12:00 | 16:00 | TRUE

## MilestonePriorities
gate_id | priority | enabled | notes
PROJECT_COMPLETE | 1 | TRUE | Default makespan objective.