## Metadata
Field | Value
project_id | AIT_DEMO_V1
project_name | AIT Planning Optimizer – Representative Demo
revision_id | DEMO_001
parent_revision
created_date | 2026-09-21
project_start | 2027-01-03
active_calendar | OMAN_HOT
objective_gate | PROJECT_COMPLETE
notes | Fictitious representative dataset for solver/UI development. No real supplier or project dates.

## Systems
Systems
Representative V1 data – fictitious / non-project data
system_id | name | family | arrival_date | delivery_state | assembly_location | installation_zone | template_version | enabled | notes
MGF | MGF | Mechanical assembly | 2027-01-10 | Parts | Staging area | CENTRAL_PAD | mechanical_v1 | TRUE | Primary support structure
TABLE | Launch Table | Mechanical assembly | 2027-01-18 | Partially assembled | Staging area | CENTRAL_PAD | mechanical_v1 | TRUE | Can be pre-assembled before MGF release
ARM | ARM | Mechanical assembly | 2027-01-20 | Parts | Staging area | CENTRAL_PAD | mechanical_v1 | TRUE | Active Release Mechanism
TGBT | TGBT | Electrical / control | 2027-01-12 | Fully assembled | Supplier | ELECTRICAL_AREA | electrical_v1 | TRUE | Main LV distribution board
GN2 | GN2 System | Packaged equipment | 2027-01-16 | Partially assembled | Supplier | FLUID_AREA | packaged_v1 | TRUE | Package + external network
LOX | LOX System | Packaged equipment | 2027-02-08 | Fully assembled | Supplier | FLUID_AREA | packaged_v1 | TRUE | Deliberately late delivery to exercise replanning

## Packages
Packages
Representative V1 data – fictitious / non-project data
package_id | system_id | name | template | enabled | display_order
MGF_INT | MGF | MGF integration | mechanical_integration | TRUE | 1
TABLE_PRE | TABLE | Launch Table pre-assembly | mechanical_preassembly | TRUE | 1
TABLE_INT | TABLE | Launch Table integration | mechanical_integration | TRUE | 2
ARM_PRE | ARM | ARM pre-assembly | mechanical_preassembly | TRUE | 1
ARM_INT | ARM | ARM integration | mechanical_integration | TRUE | 2
ARM_QUAL | ARM | ARM functional & qualification | qualification | TRUE | 3
TGBT_POS | TGBT | TGBT positioning | packaged_positioning | TRUE | 1
TGBT_COMM | TGBT | TGBT electrical commissioning | electrical_commissioning | TRUE | 2
GN2_POS | GN2 | GN2 equipment positioning | packaged_positioning | TRUE | 1
GN2_NET | GN2 | GN2 external network | fluid_network | TRUE | 2
GN2_DRY | GN2 | GN2 dry commissioning | dry_commissioning | TRUE | 3
LOX_POS | LOX | LOX container positioning | packaged_positioning | TRUE | 1
LOX_NET | LOX | LOX external network | fluid_network | TRUE | 2
LOX_CTRL | LOX | LOX electrical/control integration | electrical_commissioning | TRUE | 3
LOX_DRY | LOX | LOX dry commissioning | dry_commissioning | TRUE | 4

## Activities
Activities
Representative V1 data – fictitious / non-project data
activity_id | package_id | name | duration_h | duration_basis | preemptible | calendar_id | enabled | template_origin | is_override | notes
MGF_RECEIVE | MGF_INT | Receive / stage MGF | 4 | WORK_TIME | TRUE | OMAN_HOT | TRUE | mechanical_integration | FALSE
MGF_IQC | MGF_INT | Incoming QC | 3 | WORK_TIME | TRUE | OMAN_HOT | TRUE | mechanical_integration | FALSE
MGF_ASSEMBLY | MGF_INT | Assemble MGF | 24 | WORK_TIME | TRUE | OMAN_HOT | TRUE | mechanical_integration | FALSE | Interruptible across shifts
MGF_POSITION | MGF_INT | Position MGF | 6 | WORK_TIME | FALSE | OMAN_HOT | TRUE | mechanical_integration | FALSE | Continuous lift/positioning activity
MGF_SURVEY | MGF_INT | Topological control | 4 | WORK_TIME | FALSE | OMAN_HOT | TRUE | mechanical_integration | FALSE
MGF_FIX | MGF_INT | Adjust and fix MGF | 12 | WORK_TIME | TRUE | OMAN_HOT | TRUE | mechanical_integration | FALSE
MGF_QC | MGF_INT | Final mechanical QC | 4 | WORK_TIME | TRUE | OMAN_HOT | TRUE | mechanical_integration | FALSE
TABLE_RECEIVE | TABLE_PRE | Receive / stage table | 3 | WORK_TIME | TRUE | OMAN_HOT | TRUE | mechanical_preassembly | FALSE
TABLE_IQC | TABLE_PRE | Incoming QC | 2 | WORK_TIME | TRUE | OMAN_HOT | TRUE | mechanical_preassembly | FALSE
TABLE_PREASSY | TABLE_PRE | Pre-assemble launch table | 16 | WORK_TIME | TRUE | OMAN_HOT | TRUE | mechanical_preassembly | FALSE | Independent of MGF
TABLE_BENCH | TABLE_PRE | Bench checks | 4 | WORK_TIME | TRUE | OMAN_HOT | TRUE | mechanical_preassembly | FALSE
TABLE_POSITION | TABLE_INT | Position table on MGF | 6 | WORK_TIME | FALSE | OMAN_HOT | TRUE | mechanical_integration | TRUE | Requires released MGF
TABLE_FIX | TABLE_INT | Adjust and fix table | 8 | WORK_TIME | TRUE | OMAN_HOT | TRUE | mechanical_integration | FALSE
TABLE_QC | TABLE_INT | Final table QC | 3 | WORK_TIME | TRUE | OMAN_HOT | TRUE | mechanical_integration | FALSE
ARM_RECEIVE | ARM_PRE | Receive / stage ARM | 3 | WORK_TIME | TRUE | OMAN_HOT | TRUE | mechanical_preassembly | FALSE
ARM_IQC | ARM_PRE | Incoming QC | 3 | WORK_TIME | TRUE | OMAN_HOT | TRUE | mechanical_preassembly | FALSE
ARM_PREASSY | ARM_PRE | Pre-assemble ARM | 20 | WORK_TIME | TRUE | OMAN_HOT | TRUE | mechanical_preassembly | FALSE
ARM_BENCH | ARM_PRE | Bench mechanism checks | 6 | WORK_TIME | TRUE | OMAN_HOT | TRUE | mechanical_preassembly | FALSE
ARM_POSITION | ARM_INT | Position ARM on MGF | 8 | WORK_TIME | FALSE | OMAN_HOT | TRUE | mechanical_integration | FALSE
ARM_ALIGN | ARM_INT | Align ARM | 6 | WORK_TIME | TRUE | OMAN_HOT | TRUE | mechanical_integration | FALSE
ARM_FIX | ARM_INT | Fix ARM | 6 | WORK_TIME | TRUE | OMAN_HOT | TRUE | mechanical_integration | FALSE
ARM_QC | ARM_INT | Final ARM mechanical QC | 4 | WORK_TIME | TRUE | OMAN_HOT | TRUE | mechanical_integration | FALSE
ARM_OPEN_CLOSE | ARM_QUAL | ARM open / close functional test | 4 | WORK_TIME | FALSE | OMAN_HOT | TRUE | qualification | FALSE
ARM_VERTICAL_SIM | ARM_QUAL | Verticalization interface simulation | 6 | WORK_TIME | FALSE | OMAN_HOT | TRUE | qualification | FALSE | Exclusive central-pad operation
ARM_LOAD_TEST | ARM_QUAL | ARM load test | 8 | WORK_TIME | FALSE | OMAN_HOT | TRUE | qualification | FALSE | Exclusive central-pad operation
ARM_QUAL_REVIEW | ARM_QUAL | Qualification review / closure | 4 | WORK_TIME | TRUE | OMAN_HOT | TRUE | qualification | FALSE
TGBT_RECEIVE | TGBT_POS | Receive TGBT | 2 | WORK_TIME | TRUE | OMAN_HOT | TRUE | packaged_positioning | FALSE
TGBT_IQC | TGBT_POS | Incoming QC | 2 | WORK_TIME | TRUE | OMAN_HOT | TRUE | packaged_positioning | FALSE
TGBT_POSITION | TGBT_POS | Position TGBT | 5 | WORK_TIME | FALSE | OMAN_HOT | TRUE | packaged_positioning | FALSE
TGBT_GROUND | TGBT_COMM | Connect grounding | 3 | WORK_TIME | TRUE | OMAN_HOT | TRUE | electrical_commissioning | FALSE
TGBT_CABLE | TGBT_COMM | Connect incoming / outgoing cables | 12 | WORK_TIME | TRUE | OMAN_HOT | TRUE | electrical_commissioning | FALSE
TGBT_CHECKS | TGBT_COMM | Electrical checks | 5 | WORK_TIME | FALSE | OMAN_HOT | TRUE | electrical_commissioning | FALSE
TGBT_ENERGIZE | TGBT_COMM | Energize TGBT | 3 | WORK_TIME | FALSE | OMAN_HOT | TRUE | electrical_commissioning | FALSE
GN2_RECEIVE | GN2_POS | Receive GN2 package | 3 | WORK_TIME | TRUE | OMAN_HOT | TRUE | packaged_positioning | FALSE
GN2_IQC | GN2_POS | Incoming QC | 2 | WORK_TIME | TRUE | OMAN_HOT | TRUE | packaged_positioning | FALSE
GN2_POSITION | GN2_POS | Position GN2 package | 5 | WORK_TIME | FALSE | OMAN_HOT | TRUE | packaged_positioning | FALSE
GN2_SUPPORTS | GN2_NET | Install GN2 supports | 10 | WORK_TIME | TRUE | OMAN_HOT | TRUE | fluid_network | FALSE | Can start independently in fluid area
GN2_TUBING | GN2_NET | Install GN2 tubing | 20 | WORK_TIME | TRUE | OMAN_HOT | TRUE | fluid_network | FALSE
GN2_CONNECT | GN2_NET | Connect GN2 package to network | 6 | WORK_TIME | FALSE | OMAN_HOT | TRUE | fluid_network | FALSE | Requires package positioned and tubing installed
GN2_LEAK | GN2_NET | GN2 leak test | 6 | WORK_TIME | FALSE | OMAN_HOT | TRUE | fluid_network | FALSE
GN2_DRY_TEST | GN2_DRY | GN2 dry functional test | 6 | WORK_TIME | FALSE | OMAN_HOT | TRUE | dry_commissioning | FALSE | Requires power available
LOX_RECEIVE | LOX_POS | Receive LOX container | 4 | WORK_TIME | TRUE | OMAN_HOT | TRUE | packaged_positioning | FALSE | Late arrival
LOX_IQC | LOX_POS | Incoming QC | 3 | WORK_TIME | TRUE | OMAN_HOT | TRUE | packaged_positioning | FALSE
LOX_POSITION | LOX_POS | Position LOX container | 6 | WORK_TIME | FALSE | OMAN_HOT | TRUE | packaged_positioning | FALSE
LOX_SUPPORTS | LOX_NET | Install LOX network supports | 16 | WORK_TIME | TRUE | OMAN_HOT | TRUE | fluid_network | FALSE | Can start before container delivery
LOX_TUBING | LOX_NET | Install LOX tubing | 28 | WORK_TIME | TRUE | OMAN_HOT | TRUE | fluid_network | FALSE
LOX_CONNECT | LOX_NET | Connect LOX container to network | 8 | WORK_TIME | FALSE | OMAN_HOT | TRUE | fluid_network | FALSE | Requires container position + tubing
LOX_LEAK | LOX_NET | LOX leak / pressure test | 8 | WORK_TIME | FALSE | OMAN_HOT | TRUE | fluid_network | FALSE
LOX_CURE | LOX_NET | Sealant / anchor cure | 48 | ELAPSED_TIME | FALSE |  | True | fluid_network | TRUE | Calendar time; continues through off-shift periods
LOX_POWER | LOX_CTRL | Connect LOX power | 6 | WORK_TIME | TRUE | OMAN_HOT | TRUE | electrical_commissioning | FALSE
LOX_CONTROL | LOX_CTRL | Connect LOX controls / I/O | 10 | WORK_TIME | TRUE | OMAN_HOT | TRUE | electrical_commissioning | FALSE
LOX_IO | LOX_CTRL | LOX I/O checks | 5 | WORK_TIME | FALSE | OMAN_HOT | TRUE | electrical_commissioning | FALSE
LOX_DRY_TEST | LOX_DRY | LOX dry functional sequence | 8 | WORK_TIME | FALSE | OMAN_HOT | TRUE | dry_commissioning | FALSE
LOX_DRY_REVIEW | LOX_DRY | LOX dry review / closure | 4 | WORK_TIME | TRUE | OMAN_HOT | TRUE | dry_commissioning | FALSE

## Gates
Gates
Representative V1 data – fictitious / non-project data
gate_id | system_id | package_id | name | gate_type | exposed | is_project_milestone | notes
MGF_READY_POS | MGF | MGF_INT | MGF ready for positioning | READY_FOR_INSTALLATION | FALSE | FALSE
MGF_MECH_RELEASED | MGF | MGF_INT | MGF mechanically released | MECHANICALLY_RELEASED | TRUE | TRUE | Primary inter-system gate
TABLE_READY_INSTALL | TABLE | TABLE_PRE | Launch Table ready for installation | READY_FOR_INSTALLATION | TRUE | FALSE
TABLE_MECH_RELEASED | TABLE | TABLE_INT | Launch Table mechanically released | MECHANICALLY_RELEASED | TRUE | TRUE
ARM_READY_INSTALL | ARM | ARM_PRE | ARM ready for installation | READY_FOR_INSTALLATION | TRUE | FALSE
ARM_MECH_RELEASED | ARM | ARM_INT | ARM mechanically released | MECHANICALLY_RELEASED | TRUE | TRUE
ARM_QUALIFIED | ARM | ARM_QUAL | ARM qualified | QUALIFIED | TRUE | TRUE
TGBT_POSITIONED | TGBT | TGBT_POS | TGBT positioned | POSITIONING_RELEASED | TRUE | FALSE
POWER_AVAILABLE | TGBT | TGBT_COMM | LV power available | ELECTRICALLY_AVAILABLE | TRUE | TRUE | Enables powered commissioning
GN2_POSITIONED | GN2 | GN2_POS | GN2 package positioned | POSITIONING_RELEASED | TRUE | FALSE
GN2_NETWORK_DRY | GN2 | GN2_NET | GN2 network dry released | DRY_RELEASED | TRUE | FALSE
GN2_DRY_RELEASED | GN2 | GN2_DRY | GN2 system dry released | FUNCTIONALLY_RELEASED | TRUE | TRUE
LOX_POSITIONED | LOX | LOX_POS | LOX container positioned | POSITIONING_RELEASED | TRUE | FALSE
LOX_NETWORK_DRY | LOX | LOX_NET | LOX network dry released | DRY_RELEASED | TRUE | FALSE
LOX_CONTROLS_AVAILABLE | LOX | LOX_CTRL | LOX controls available | ELECTRICALLY_AVAILABLE | TRUE | FALSE
LOX_DRY_RELEASED | LOX | LOX_DRY | LOX system dry released | FUNCTIONALLY_RELEASED | TRUE | TRUE
PROJECT_COMPLETE |  |  | Representative project complete | PROJECT_COMPLETE | TRUE | TRUE | Convergence of demo completion gates

## Dependencies
Dependencies
Representative V1 data – fictitious / non-project data
dependency_id | source_type | source_id | target_type | target_id | relation | lag_h | enabled | rationale
D001 | ACTIVITY | MGF_RECEIVE | ACTIVITY | MGF_IQC | FS | 0 | TRUE
D002 | ACTIVITY | MGF_IQC | ACTIVITY | MGF_ASSEMBLY | FS | 0 | TRUE
D003 | ACTIVITY | MGF_ASSEMBLY | ACTIVITY | MGF_POSITION | FS | 0 | TRUE
D004 | ACTIVITY | MGF_POSITION | ACTIVITY | MGF_SURVEY | FS | 0 | TRUE
D005 | ACTIVITY | MGF_SURVEY | ACTIVITY | MGF_FIX | FS | 0 | TRUE
D006 | ACTIVITY | MGF_FIX | ACTIVITY | MGF_QC | FS | 0 | TRUE
D007 | ACTIVITY | TABLE_RECEIVE | ACTIVITY | TABLE_IQC | FS | 0 | TRUE
D008 | ACTIVITY | TABLE_IQC | ACTIVITY | TABLE_PREASSY | FS | 0 | TRUE
D009 | ACTIVITY | TABLE_PREASSY | ACTIVITY | TABLE_BENCH | FS | 0 | TRUE
D010 | ACTIVITY | TABLE_POSITION | ACTIVITY | TABLE_FIX | FS | 0 | TRUE
D011 | ACTIVITY | TABLE_FIX | ACTIVITY | TABLE_QC | FS | 0 | TRUE
D012 | ACTIVITY | ARM_RECEIVE | ACTIVITY | ARM_IQC | FS | 0 | TRUE
D013 | ACTIVITY | ARM_IQC | ACTIVITY | ARM_PREASSY | FS | 0 | TRUE
D014 | ACTIVITY | ARM_PREASSY | ACTIVITY | ARM_BENCH | FS | 0 | TRUE
D015 | ACTIVITY | ARM_POSITION | ACTIVITY | ARM_ALIGN | FS | 0 | TRUE
D016 | ACTIVITY | ARM_ALIGN | ACTIVITY | ARM_FIX | FS | 0 | TRUE
D017 | ACTIVITY | ARM_FIX | ACTIVITY | ARM_QC | FS | 0 | TRUE
D018 | ACTIVITY | ARM_OPEN_CLOSE | ACTIVITY | ARM_VERTICAL_SIM | FS | 0 | TRUE
D019 | ACTIVITY | ARM_VERTICAL_SIM | ACTIVITY | ARM_LOAD_TEST | FS | 0 | TRUE
D020 | ACTIVITY | ARM_LOAD_TEST | ACTIVITY | ARM_QUAL_REVIEW | FS | 0 | TRUE
D021 | ACTIVITY | TGBT_RECEIVE | ACTIVITY | TGBT_IQC | FS | 0 | TRUE
D022 | ACTIVITY | TGBT_IQC | ACTIVITY | TGBT_POSITION | FS | 0 | TRUE
D023 | ACTIVITY | TGBT_GROUND | ACTIVITY | TGBT_CABLE | FS | 0 | TRUE
D024 | ACTIVITY | TGBT_CABLE | ACTIVITY | TGBT_CHECKS | FS | 0 | TRUE
D025 | ACTIVITY | TGBT_CHECKS | ACTIVITY | TGBT_ENERGIZE | FS | 0 | TRUE
D026 | ACTIVITY | GN2_RECEIVE | ACTIVITY | GN2_IQC | FS | 0 | TRUE
D027 | ACTIVITY | GN2_IQC | ACTIVITY | GN2_POSITION | FS | 0 | TRUE
D028 | ACTIVITY | GN2_SUPPORTS | ACTIVITY | GN2_TUBING | FS | 0 | TRUE
D029 | ACTIVITY | GN2_TUBING | ACTIVITY | GN2_CONNECT | FS | 0 | TRUE
D030 | ACTIVITY | GN2_CONNECT | ACTIVITY | GN2_LEAK | FS | 0 | TRUE
D031 | ACTIVITY | LOX_RECEIVE | ACTIVITY | LOX_IQC | FS | 0 | TRUE
D032 | ACTIVITY | LOX_IQC | ACTIVITY | LOX_POSITION | FS | 0 | TRUE
D033 | ACTIVITY | LOX_SUPPORTS | ACTIVITY | LOX_TUBING | FS | 0 | TRUE
D034 | ACTIVITY | LOX_TUBING | ACTIVITY | LOX_CONNECT | FS | 0 | TRUE
D035 | ACTIVITY | LOX_CONNECT | ACTIVITY | LOX_LEAK | FS | 0 | TRUE
D036 | ACTIVITY | LOX_LEAK | ACTIVITY | LOX_CURE | FS | 0 | TRUE
D037 | ACTIVITY | LOX_POWER | ACTIVITY | LOX_CONTROL | FS | 0 | TRUE
D038 | ACTIVITY | LOX_CONTROL | ACTIVITY | LOX_IO | FS | 0 | TRUE
D039 | ACTIVITY | LOX_DRY_TEST | ACTIVITY | LOX_DRY_REVIEW | FS | 0 | TRUE
D040 | ACTIVITY | MGF_ASSEMBLY | GATE | MGF_READY_POS | FS | 0 | TRUE
D041 | ACTIVITY | MGF_QC | GATE | MGF_MECH_RELEASED | FS | 0 | TRUE
D042 | ACTIVITY | TABLE_BENCH | GATE | TABLE_READY_INSTALL | FS | 0 | TRUE
D043 | ACTIVITY | TABLE_QC | GATE | TABLE_MECH_RELEASED | FS | 0 | TRUE
D044 | ACTIVITY | ARM_BENCH | GATE | ARM_READY_INSTALL | FS | 0 | TRUE
D045 | ACTIVITY | ARM_QC | GATE | ARM_MECH_RELEASED | FS | 0 | TRUE
D046 | ACTIVITY | ARM_QUAL_REVIEW | GATE | ARM_QUALIFIED | FS | 0 | TRUE
D047 | ACTIVITY | TGBT_POSITION | GATE | TGBT_POSITIONED | FS | 0 | TRUE
D048 | ACTIVITY | TGBT_ENERGIZE | GATE | POWER_AVAILABLE | FS | 0 | TRUE
D049 | ACTIVITY | GN2_POSITION | GATE | GN2_POSITIONED | FS | 0 | TRUE
D050 | ACTIVITY | GN2_LEAK | GATE | GN2_NETWORK_DRY | FS | 0 | TRUE
D051 | ACTIVITY | GN2_DRY_TEST | GATE | GN2_DRY_RELEASED | FS | 0 | TRUE
D052 | ACTIVITY | LOX_POSITION | GATE | LOX_POSITIONED | FS | 0 | TRUE
D053 | ACTIVITY | LOX_CURE | GATE | LOX_NETWORK_DRY | FS | 0 | TRUE
D054 | ACTIVITY | LOX_IO | GATE | LOX_CONTROLS_AVAILABLE | FS | 0 | TRUE
D055 | ACTIVITY | LOX_DRY_REVIEW | GATE | LOX_DRY_RELEASED | FS | 0 | TRUE
D056 | GATE | MGF_READY_POS | ACTIVITY | MGF_POSITION | FS | 0 | TRUE | Assembly complete before pad positioning
D057 | GATE | TABLE_READY_INSTALL | ACTIVITY | TABLE_POSITION | FS | 0 | TRUE | Pre-assembly can finish independently
D058 | GATE | MGF_MECH_RELEASED | ACTIVITY | TABLE_POSITION | FS | 0 | TRUE | Table mounts on released MGF
D059 | GATE | ARM_READY_INSTALL | ACTIVITY | ARM_POSITION | FS | 0 | TRUE | ARM pre-assembly complete
D060 | GATE | MGF_MECH_RELEASED | ACTIVITY | ARM_POSITION | FS | 0 | TRUE | ARM final integration requires MGF
D061 | GATE | ARM_MECH_RELEASED | ACTIVITY | ARM_OPEN_CLOSE | FS | 0 | TRUE | Qualification starts after mechanical release
D062 | GATE | TGBT_POSITIONED | ACTIVITY | TGBT_GROUND | FS | 0 | TRUE | Position before electrical commissioning
D063 | GATE | GN2_POSITIONED | ACTIVITY | GN2_CONNECT | FS | 0 | TRUE | Package must be positioned before final network connection
D064 | GATE | POWER_AVAILABLE | ACTIVITY | GN2_DRY_TEST | FS | 0 | TRUE | Powered dry test requires LV power
D065 | GATE | GN2_NETWORK_DRY | ACTIVITY | GN2_DRY_TEST | FS | 0 | TRUE | Network release prerequisite
D066 | GATE | LOX_POSITIONED | ACTIVITY | LOX_CONNECT | FS | 0 | TRUE | Container must be positioned before final connection
D067 | GATE | TGBT_POSITIONED | ACTIVITY | LOX_POWER | FS | 0 | TRUE | TGBT physically available
D068 | GATE | POWER_AVAILABLE | ACTIVITY | LOX_IO | FS | 0 | TRUE | Powered I/O checks
D069 | GATE | LOX_NETWORK_DRY | ACTIVITY | LOX_DRY_TEST | FS | 0 | TRUE | Network release prerequisite
D070 | GATE | LOX_CONTROLS_AVAILABLE | ACTIVITY | LOX_DRY_TEST | FS | 0 | TRUE | Controls prerequisite
D071 | GATE | TABLE_MECH_RELEASED | GATE | PROJECT_COMPLETE | FS | 0 | TRUE | Representative completion prerequisite
D072 | GATE | ARM_QUALIFIED | GATE | PROJECT_COMPLETE | FS | 0 | TRUE | Representative completion prerequisite
D073 | GATE | GN2_DRY_RELEASED | GATE | PROJECT_COMPLETE | FS | 0 | TRUE | Representative completion prerequisite
D074 | GATE | LOX_DRY_RELEASED | GATE | PROJECT_COMPLETE | FS | 0 | TRUE | Representative completion prerequisite

## Resources
Resources
Representative V1 data – fictitious / non-project data
resource_id | name | type | capacity | calendar_id | unlimited | notes
QUALITY | Quality | HUMAN | 2 | OMAN_HOT | FALSE | Two interchangeable quality inspectors
OPERATOR | Operator | HUMAN | 4 | OMAN_HOT | FALSE | General operations team
CRANE_OPERATOR | Crane operator | HUMAN | 1 | OMAN_HOT | FALSE | No substitution by default
FORKLIFT_OPERATOR | Forklift operator | HUMAN | 2 | OMAN_HOT | FALSE
SURVEYOR | Surveyor | HUMAN | 1 | OMAN_HOT | FALSE
MECH_CONTRACTOR | Mechanical contractor | HUMAN | 12 | OMAN_HOT | FALSE | Representative capacity
ELEC_CONTRACTOR | Electrical contractor | HUMAN | 5 | OMAN_HOT | FALSE
FLUID_CONTRACTOR | Fluid contractor | HUMAN | 8 | OMAN_HOT | FALSE
CRANE | Crane | EQUIPMENT | 1 | OMAN_HOT | FALSE
FORKLIFT | Forklift | EQUIPMENT | 2 | OMAN_HOT | FALSE

## ActivityResources
ActivityResources
Representative V1 data – fictitious / non-project data
activity_id | resource_id | quantity
MGF_RECEIVE | OPERATOR | 2
MGF_RECEIVE | FORKLIFT_OPERATOR | 1
MGF_RECEIVE | FORKLIFT | 1
MGF_IQC | QUALITY | 1
MGF_IQC | OPERATOR | 1
MGF_ASSEMBLY | MECH_CONTRACTOR | 6
MGF_ASSEMBLY | OPERATOR | 1
MGF_POSITION | MECH_CONTRACTOR | 4
MGF_POSITION | OPERATOR | 2
MGF_POSITION | CRANE_OPERATOR | 1
MGF_POSITION | CRANE | 1
MGF_SURVEY | SURVEYOR | 1
MGF_SURVEY | QUALITY | 1
MGF_SURVEY | OPERATOR | 1
MGF_FIX | MECH_CONTRACTOR | 4
MGF_FIX | OPERATOR | 1
MGF_QC | QUALITY | 1
MGF_QC | OPERATOR | 1
TABLE_RECEIVE | OPERATOR | 2
TABLE_RECEIVE | FORKLIFT_OPERATOR | 1
TABLE_RECEIVE | FORKLIFT | 1
TABLE_IQC | QUALITY | 1
TABLE_PREASSY | MECH_CONTRACTOR | 4
TABLE_BENCH | QUALITY | 1
TABLE_BENCH | MECH_CONTRACTOR | 2
TABLE_POSITION | MECH_CONTRACTOR | 3
TABLE_POSITION | OPERATOR | 2
TABLE_POSITION | CRANE_OPERATOR | 1
TABLE_POSITION | CRANE | 1
TABLE_FIX | MECH_CONTRACTOR | 3
TABLE_QC | QUALITY | 1
ARM_RECEIVE | OPERATOR | 2
ARM_RECEIVE | FORKLIFT_OPERATOR | 1
ARM_RECEIVE | FORKLIFT | 1
ARM_IQC | QUALITY | 1
ARM_PREASSY | MECH_CONTRACTOR | 5
ARM_BENCH | QUALITY | 1
ARM_BENCH | MECH_CONTRACTOR | 2
ARM_POSITION | MECH_CONTRACTOR | 4
ARM_POSITION | OPERATOR | 2
ARM_POSITION | CRANE_OPERATOR | 1
ARM_POSITION | CRANE | 1
ARM_ALIGN | SURVEYOR | 1
ARM_ALIGN | MECH_CONTRACTOR | 2
ARM_FIX | MECH_CONTRACTOR | 3
ARM_QC | QUALITY | 1
ARM_OPEN_CLOSE | QUALITY | 1
ARM_OPEN_CLOSE | OPERATOR | 2
ARM_OPEN_CLOSE | MECH_CONTRACTOR | 2
ARM_VERTICAL_SIM | QUALITY | 1
ARM_VERTICAL_SIM | OPERATOR | 3
ARM_VERTICAL_SIM | MECH_CONTRACTOR | 3
ARM_VERTICAL_SIM | CRANE_OPERATOR | 1
ARM_VERTICAL_SIM | CRANE | 1
ARM_LOAD_TEST | QUALITY | 2
ARM_LOAD_TEST | OPERATOR | 3
ARM_LOAD_TEST | MECH_CONTRACTOR | 3
ARM_QUAL_REVIEW | QUALITY | 1
TGBT_RECEIVE | OPERATOR | 1
TGBT_RECEIVE | FORKLIFT_OPERATOR | 1
TGBT_RECEIVE | FORKLIFT | 1
TGBT_IQC | QUALITY | 1
TGBT_IQC | ELEC_CONTRACTOR | 1
TGBT_POSITION | OPERATOR | 2
TGBT_POSITION | CRANE_OPERATOR | 1
TGBT_POSITION | CRANE | 1
TGBT_GROUND | ELEC_CONTRACTOR | 2
TGBT_CABLE | ELEC_CONTRACTOR | 4
TGBT_CHECKS | ELEC_CONTRACTOR | 2
TGBT_CHECKS | QUALITY | 1
TGBT_ENERGIZE | ELEC_CONTRACTOR | 2
TGBT_ENERGIZE | QUALITY | 1
TGBT_ENERGIZE | OPERATOR | 1
GN2_RECEIVE | OPERATOR | 1
GN2_RECEIVE | FORKLIFT_OPERATOR | 1
GN2_RECEIVE | FORKLIFT | 1
GN2_IQC | QUALITY | 1
GN2_IQC | FLUID_CONTRACTOR | 1
GN2_POSITION | OPERATOR | 2
GN2_POSITION | CRANE_OPERATOR | 1
GN2_POSITION | CRANE | 1
GN2_SUPPORTS | FLUID_CONTRACTOR | 3
GN2_TUBING | FLUID_CONTRACTOR | 4
GN2_CONNECT | FLUID_CONTRACTOR | 3
GN2_CONNECT | QUALITY | 1
GN2_LEAK | FLUID_CONTRACTOR | 2
GN2_LEAK | QUALITY | 1
GN2_DRY_TEST | FLUID_CONTRACTOR | 2
GN2_DRY_TEST | ELEC_CONTRACTOR | 1
GN2_DRY_TEST | QUALITY | 1
GN2_DRY_TEST | OPERATOR | 1
LOX_RECEIVE | OPERATOR | 2
LOX_RECEIVE | FORKLIFT_OPERATOR | 1
LOX_RECEIVE | FORKLIFT | 1
LOX_IQC | QUALITY | 1
LOX_IQC | FLUID_CONTRACTOR | 1
LOX_POSITION | OPERATOR | 2
LOX_POSITION | CRANE_OPERATOR | 1
LOX_POSITION | CRANE | 1
LOX_SUPPORTS | FLUID_CONTRACTOR | 3
LOX_TUBING | FLUID_CONTRACTOR | 5
LOX_CONNECT | FLUID_CONTRACTOR | 3
LOX_CONNECT | QUALITY | 1
LOX_LEAK | FLUID_CONTRACTOR | 2
LOX_LEAK | QUALITY | 1
LOX_POWER | ELEC_CONTRACTOR | 2
LOX_CONTROL | ELEC_CONTRACTOR | 3
LOX_IO | ELEC_CONTRACTOR | 2
LOX_IO | QUALITY | 1
LOX_DRY_TEST | FLUID_CONTRACTOR | 2
LOX_DRY_TEST | ELEC_CONTRACTOR | 1
LOX_DRY_TEST | QUALITY | 2
LOX_DRY_TEST | OPERATOR | 2
LOX_DRY_REVIEW | QUALITY | 1

## Zones
Zones
Representative V1 data – fictitious / non-project data
zone_id | name | capacity | calendar_id | notes
CENTRAL_PAD | Central pad | 4 |  | Generic workfront capacity
FLUID_AREA | Fluid area | 5
ELECTRICAL_AREA | Electrical area | 3
STAGING_AREA | Staging area | 10
CRANE_CORRIDOR | Crane corridor | 1 |  | Exclusive for major lifts

## ActivityZones
ActivityZones
Representative V1 data – fictitious / non-project data
activity_id | zone_id | load | exclusive
MGF_RECEIVE | STAGING_AREA | 1 | FALSE
MGF_IQC | STAGING_AREA | 1 | FALSE
MGF_ASSEMBLY | STAGING_AREA | 1 | FALSE
TABLE_RECEIVE | STAGING_AREA | 1 | FALSE
TABLE_IQC | STAGING_AREA | 1 | FALSE
TABLE_PREASSY | STAGING_AREA | 1 | FALSE
TABLE_BENCH | STAGING_AREA | 1 | FALSE
ARM_RECEIVE | STAGING_AREA | 1 | FALSE
ARM_IQC | STAGING_AREA | 1 | FALSE
ARM_PREASSY | STAGING_AREA | 1 | FALSE
ARM_BENCH | STAGING_AREA | 1 | FALSE
MGF_POSITION | CENTRAL_PAD | 1 | FALSE
MGF_SURVEY | CENTRAL_PAD | 1 | FALSE
MGF_FIX | CENTRAL_PAD | 1 | FALSE
MGF_QC | CENTRAL_PAD | 1 | FALSE
TABLE_POSITION | CENTRAL_PAD | 1 | FALSE
TABLE_FIX | CENTRAL_PAD | 1 | FALSE
TABLE_QC | CENTRAL_PAD | 1 | FALSE
ARM_POSITION | CENTRAL_PAD | 1 | FALSE
ARM_ALIGN | CENTRAL_PAD | 1 | FALSE
ARM_FIX | CENTRAL_PAD | 1 | FALSE
ARM_QC | CENTRAL_PAD | 1 | FALSE
ARM_OPEN_CLOSE | CENTRAL_PAD | 1 | FALSE
ARM_VERTICAL_SIM | CENTRAL_PAD | ALL | TRUE
ARM_LOAD_TEST | CENTRAL_PAD | ALL | TRUE
MGF_POSITION | CRANE_CORRIDOR | ALL | TRUE
TABLE_POSITION | CRANE_CORRIDOR | ALL | TRUE
ARM_POSITION | CRANE_CORRIDOR | ALL | TRUE
TGBT_POSITION | CRANE_CORRIDOR | ALL | TRUE
GN2_POSITION | CRANE_CORRIDOR | ALL | TRUE
LOX_POSITION | CRANE_CORRIDOR | ALL | TRUE
ARM_VERTICAL_SIM | CRANE_CORRIDOR | ALL | TRUE
TGBT_RECEIVE | ELECTRICAL_AREA | 1 | FALSE
TGBT_IQC | ELECTRICAL_AREA | 1 | FALSE
TGBT_GROUND | ELECTRICAL_AREA | 1 | FALSE
TGBT_CABLE | ELECTRICAL_AREA | 1 | FALSE
TGBT_CHECKS | ELECTRICAL_AREA | 1 | FALSE
TGBT_ENERGIZE | ELECTRICAL_AREA | 1 | FALSE
GN2_RECEIVE | FLUID_AREA | 1 | FALSE
GN2_IQC | FLUID_AREA | 1 | FALSE
GN2_SUPPORTS | FLUID_AREA | 1 | FALSE
GN2_TUBING | FLUID_AREA | 1 | FALSE
GN2_CONNECT | FLUID_AREA | 1 | FALSE
GN2_LEAK | FLUID_AREA | 1 | FALSE
GN2_DRY_TEST | FLUID_AREA | 1 | FALSE
LOX_RECEIVE | FLUID_AREA | 1 | FALSE
LOX_IQC | FLUID_AREA | 1 | FALSE
LOX_SUPPORTS | FLUID_AREA | 1 | FALSE
LOX_TUBING | FLUID_AREA | 1 | FALSE
LOX_CONNECT | FLUID_AREA | 1 | FALSE
LOX_LEAK | FLUID_AREA | 1 | FALSE
LOX_CURE | FLUID_AREA | 1 | FALSE
LOX_POWER | FLUID_AREA | 1 | FALSE
LOX_CONTROL | FLUID_AREA | 1 | FALSE
LOX_IO | FLUID_AREA | 1 | FALSE
LOX_DRY_TEST | FLUID_AREA | 1 | FALSE
LOX_DRY_REVIEW | FLUID_AREA | 1 | FALSE

## Calendars
Calendars
Representative V1 data – fictitious / non-project data
calendar_id | name | timezone | valid_from | valid_to | weekend_days | notes
OMAN_HOT | Oman hot-season site calendar | Asia/Muscat | 2027-01-01 | 2027-12-31 | FRI,SAT | Demo calendar; two work windows per working day
OMAN_COOL | Oman cool-season site calendar | Asia/Muscat | 2027-01-01 | 2027-12-31 | FRI,SAT | Alternative calendar for later testing

## CalendarShifts
CalendarShifts
Representative V1 data – fictitious / non-project data
calendar_id | weekday | shift_name | start_time | end_time | enabled
OMAN_HOT | SUN | Morning | 05:00 | 11:00 | TRUE
OMAN_HOT | SUN | Night | 18:00 | 00:00 | TRUE
OMAN_COOL | SUN | Day | 07:00 | 17:00 | TRUE
OMAN_HOT | MON | Morning | 05:00 | 11:00 | TRUE
OMAN_HOT | MON | Night | 18:00 | 00:00 | TRUE
OMAN_COOL | MON | Day | 07:00 | 17:00 | TRUE
OMAN_HOT | TUE | Morning | 05:00 | 11:00 | TRUE
OMAN_HOT | TUE | Night | 18:00 | 00:00 | TRUE
OMAN_COOL | TUE | Day | 07:00 | 17:00 | TRUE
OMAN_HOT | WED | Morning | 05:00 | 11:00 | TRUE
OMAN_HOT | WED | Night | 18:00 | 00:00 | TRUE
OMAN_COOL | WED | Day | 07:00 | 17:00 | TRUE
OMAN_HOT | THU | Morning | 05:00 | 11:00 | TRUE
OMAN_HOT | THU | Night | 18:00 | 00:00 | TRUE
OMAN_COOL | THU | Day | 07:00 | 17:00 | TRUE

## MilestonePriorities
MilestonePriorities
Representative V1 data – fictitious / non-project data
gate_id | priority | enabled | notes
PROJECT_COMPLETE | 1 | TRUE | Default optimization objective
ARM_QUALIFIED |  | FALSE | Enable as higher-priority milestone when desired
GN2_DRY_RELEASED |  | FALSE
LOX_DRY_RELEASED |  | FALSE
POWER_AVAILABLE |  | FALSE

## ResourceSubstitutions
ResourceSubstitutions
Representative V1 data – fictitious / non-project data
required_resource_id | substitute_resource_id | conversion_ratio | enabled | notes
OPERATOR | MECH_CONTRACTOR | 1 | FALSE | Example only; disabled by default

## DataDictionary
DataDictionary
Representative V1 data – fictitious / non-project data
Entity | Purpose | Key fields / V1 rule
System | Logical equipment/system container | family, arrival_date, delivery_state, assembly_location
Package | AIT work package within a system | template, enabled, display_order
Activity | Atomic scheduling unit | duration_h, WORK_TIME/ELAPSED_TIME, preemptible
Gate | Zero-duration state / convergence point | gate_type, exposed
Dependency | Single source of truth for precedence | source, target, FS, optional lag_h
Resource | Human/equipment/workfront capacity | capacity, calendar_id
Zone | Capacitated physical area | capacity; exclusivity is requested by activities
Calendar | Working windows / seasonal shifts | weekly shifts + validity period
Milestone priority | Lexicographic optimization target | priority 1 first, then 2, etc.